## Sheet1
Week | Task | Start | End
Week 5 | Background Research and User Persona Definition | 2025-12-05 | 18/05/2025
Week 6 | Literature Review and Related Work Analysis | 19/05/2025 | 25/05/2025
Week 7 | Project Planning for Timeline and Evaluation Strategy, System Design (Architecture, Data Model, API Specification) | 26/05/2025 | 2025-01-06
Week 8 | Frontend Setup (React), Initial Page Routing, Implement Dashboards | 2025-02-06 | 2025-08-06
Week 9 | Backend Setup (Express.js, SQLite), Authentication, JWT | 2025-09-06 | 15/06/2025
Week 10 | Preliminary Report Submission, Player CRUD & Visibility API, Role-based Access Prototype | 16/06/2025 | 22/06/2025
Week 11 | Backend Setup (Express.js, SQLite), Authentication, JWT | 23/06/2025 | 29/06/2025
Week 12 | UI Improvements, Centralized Roles, Logout Handling | 30/06/2025 | 2025-06-07
Week 13 | Token Expiry Handling, Role Context Mapping, Frontend Feedback Handling, Page Styling | 2025-07-07 | 13/07/2025
Week 14 | Academic Writing | 14/07/2025 | 20/07/2025
Week 15 | Academic Writing | 21/07/2025 | 27/07/2025
Week 16 | Finalizing Questionnaire & Evaluation Plan | 28/07/2025 | 2025-03-08
Week 17 | Project Testing, Mock User Evaluation via Questionnaire | 2025-04-08 | 2025-10-08
Week 18 | Submit Draft Report | 2025-11-08 | 17/08/2025
Week 19 | Project Video Demo Preparation & Evaluation | 18/08/2025 | 24/08/2025
Week 20 | Project Video Demo Preparation & Evaluation | 25/08/2025 | 31/08/2025
Week 22 | Submit Final Report & Project | 15/09/2025